# THE OS/360 DEBACLE

Robert McMordie

This document is copyright 1997-98 Robert McMordie.

The text in this document may not be reproduced in any form without my prior consent. I can be contacted at r.j.mcmordie@bcs.org.uk.

Document revision 1 (5th November 1998).

THE OS/360 DEBACLE

1. INTRODUCTION

In 1967 IBM released OS/360, the operating system for its successful System/360 range of computers. It was a year late and was full of problems and bugs 1. Its development had been the biggest software development debacle of the decade, and was a sign of the impending software crisis. In this essay, I will first present some background about the System/360, then I will examine the development of OS/360, the problems encountered and the lessons learnt.

2. THE SPREAD REPORT

At the start of the 1960's, IBM were facing a dilemma. There were seven different ranges of computer available, requiring over 2500 different circuit modules 8. Some of the machines were used for scientific purposes, others for data processing. Also each of the systems also had its own pieces of software that had to be maintained. This was a more serious problem as none of the computers could run software that was written for one of the other systems. Moreover, the situation was about to get worse. IBM were planning to manufacture a number of new systems, including additions to the existing 7000 series of computers that were to be developed at their Data Systems Division (DSD) at Poughkeepsie 2. As DSD was already responsible for the 701 and 702 ranges of computers, many people at DSD felt that this would present too much variety in the available systems. So, in mid-1960, the 8000 series of computers was born 5.

The 8000 series was a family of processors, starting at the bottom of the range with low-power systems and becoming increasingly powerful higher up the range. However, the processors were not compatible with each other. To add to the confusion, other systems were also being developed, including the 1410 (a system, based on the 1401), the 1620 and a machine codenamed SCAMP, that was being developed at IBM Hursley 2. In January 1961, the 8000 series was presented to senior management within IBM. By February, it had been decided that the series should not be announced. Instead, a number of new versions of the 1410 and 7090 computers would be released as stopgap systems, and a new start should be made, on a "total cohesive product line" 2.

To try to resolve the compatibility issues, the SPREAD (Systems Programming, Research, Engineering And Development) task group was formed in October 1961. The SPREAD team comprised thirteen representatives of engineering, software and marketing. They started work at the beginning of November 1961 and two months later, they had produced an 80 page document, the SPREAD Report 1.

This report was one of the most significant documents written in the history of IBM at that point. It was intended to establish the direction of IBM's data processing products for the next decade 1 and to rationalise the existing ranges 9. In fact, it has dictated the architecture of mainframes since the mid-1960's. In the introduction, the report states :

The SPREAD activity was initiated to establish an overall IBM plan for data processor products. The plan is to encompass all stored-program processor developments in IBM, is to extend to 1970, and must consider the following factors... 3

The report recommended that a new family of five compatible processors should be released, the New Product Line (NPL) 3. A large number of recommendations are also made about the design of the processor, the software required, marketing and implementation. The report was presented to IBM Senior Management in New York, on 4th January 1962 1. Despite those present at the meeting being unenthusiastic about the NPL, it was decided to begin development on the five processors 2.

3. THE IBM SYSTEM/360

Development started on the NPL in the spring of 1962 2. This was split between three development sites. Poughkeepsie (DSD) would work on the three most powerful processors, Hursley getting the next one down and Endicott (GPD) getting the least powerful 5, 9. A large portion of 1962 was spent deciding on the processor architecture and creating an architecture manual 2. It was finalised in October. It had four main innovations. These were described in 1964 6 as an approach to storage that allowed great flexibility, a flexible I/O system capable of concurrent operation, a general-purpose machine architecture and strict upward and downward machine-language compatibility. The end of 1962 and much of 1963 was spent developing improved versions of existing components and completely new systems, and starting the manufacturing process 2. There were many problems that had to dealt with, mainly concerned with the availability of the SLT circuitry to be used in the systems. Another problem occurred with the definition of the three models in the middle of the range. It was fairly clear what the performance of the models at the top and bottom end of the range needed to be, but much less well-defined for the other three systems.

In late 1963, with the NPL nearing completion, IBM started to think about a launch strategy for the range, now named System/360 1. A plan was devised, calling for its introduction over a 15 month period, starting in January 1964 2. This plan was soon changed, following an announcement by Honeywell in December 1963 1, unveiling their H-200 computer. This was compatible with the 1401 system, but offered much better performance for the same price. As a result, IBM moved the launch dates so all the computers were launched simultaneously on 7th April 1964 2. The initial range comprised the Model 30 (the Endicott machine), Model 40 (the Hursley machine), Model 50, Model 60, Model 62 (almost identical to the Model 60, using the same processor but with faster memory) and Model 70 (all from Poughkeepsie), along with a range of 44 peripherals. The first deliveries of the System/360 hardware was the Model 40 in April 1965. In the time since the initial announcement, the range had changed slightly. Models 60 and 62 had become the faster Model 65, and Model 70 had been replaced by Model 75 2. The range continued to develop throughout the late 1960s, one of the additions being a timesharing system (the Model 67). It did much to shape the mainframe industry for many years to come. It was not superseeded until June 1970, when the IBM System/370 was announced 1.

The major problem that IBM faced with System/360 development was a software issues associated with the development of the operating system, OS/360. In the remainder of this essay, I will look at some of these problems, how they were addressed and some of the lessons learnt from this experience by both IBM and the industry as a whole.

4. DESIGN AND EARLY DEVELOPMENT OF OS/360 - 1962 to 1963

4.1. INITIAL DESIGN

The initial development of OS/360 started in 1962 2. It got off to a bad start. A request was sent to the DSD programming department, asking for experienced programmers to participate in the system architecture design. However, all the programmers were already occupied, writing system software for IBM's existing range of products. Finally, the manager of the Programming Systems department at DSD agreed to appoint George Grover, as programming manager, part time for the NPL.

The first issue that addressed Grover was the number of operating systems that would be required 2. It was decided that three operating systems would be needed, to cater for System/360 machines. These were labelled with Roman numerals, II, III and IV. Roman numeral I was used for card systems with very small amounts of memory, and no disc or tape peripherals. Grover then formulated rough ideas about what each system should be able to do, and allocated development sites. Endicott was to implement numbers I and II, Hursley number III and Poughkeepsie number IV. The development plan soon became known as the Four Romans.

In January 1963, a meeting was held in Poughkeepsie, to flesh out the preliminary specifications already developed 2. This included specification of the processor features needed and amount of memory. Following this a table was created by Richard Case, the first engineering manager of the NPL 400 processor with a column for each of the four systems to be developed. The table rows listed the various features that were to be implemented in the systems. This table, named the "map of the world" 2, contained information about the features needed in each of the systems. From this the programming objectives for the NPL project were determined. As early as late 1962, Case wrote a memorandum critical of the NPL integrated plan, citing programming at the top of the problem list.

4.2. THE PROBLEMS CONTINUE

By the end of March, the software developers at Poughkeepsie were ready to progress to the next stage of definition of the software, written specifications defining use and function 2. They were following a plan, written at the end of 1962, that aimed to keep software development in line with engineering development. It was at this point that the next problem occurred. An enhanced IBM 7090/7094 operating system was due to have been released in November 1962 2. However, the release had been delayed and rescheduled for March 1963. Similar delays were anticipated for the 7040/7044 operating system. Both these operating systems were being implemented at Poughkeepsie. Additionally, at Endicott and San Jose, new releases in two existing ranges were being readied for release, and software was needed for thesel. As a result of these demands, a large number of programmers were assigned to these projects, at a time when more programmers were needed for the NPL software specification.

In February 1963, Brooks announced that there would be a six week delay in the specification of the next level of NPL software 2. He also took the opportunity to inform three levels of superiors that there had been a failure in the DSD programming department to recognise a "responsible implementing authority" 2. Because of the internal structure of the DSD programming department, no single manager was able to take overall responsibility for NPL software development. Brooks' comment resulted in a reorganisation and the formation of Programming Development, to be headed by Carl Reynolds. Programming was then divided internally, into NPL programming, headed by Robert Ruthrauff, and current product support.

This reorganisation coincided with yet another problem. An audit committee had been convened by Robert Evans, Development Vice President of the DSD, to evaluate progress 2. The committee warned that too much independence was being given to the  laboratories responsible for designing the Romans, and that this would reduce the advantage given by making the range of processors compatible. They also suggested object code compatibility between the processors should be a target. Brooks agreed with the committee, but Grover supported source program compatibility, arguing that object code compatibility would be too difficult to achieve. Despite his objections, in January 1963 Grover was instructed by Brooks that application programs "compiled or assembled for any of the first three systems must run under any larger system." 2

Following the reorganisation in February, Ruthrauff's team were given the task of adding more detail to the plan established by Grover 2. This resulted in the memory allocation for each Roman being doubled.

4.3. REVISION OF IDEAS

In April 1963, a small number of programmers became available to join the NPL planning team. A hierarchy of three councils was formed 2. This caused a slow down of the design process, as the newly joined programmers had come from very different projects. A major change occurred at this point, due to the large range of I/O devices to be supported by Romans II and III. As a result they were each split into two further systems and the Romans renamed as the M-systems, M standing for "monitor", M1 to M6.

At about this time, mid-1963, the Federal Systems Division (FSD) presented an alternative plan 2. They had been asked by Grover, in mid-1962, to conduct a study of an operating system that would allow users to connect to a central system via communication lines. In July 1963, the FSD team published a report proposing a multiprogramming system 2.

The FSD report was taken at a meeting in August, together with the M-plan and an additional plan similar to the FSD one, but not quite as well defined. No major decision was made at the meeting. In spite of this the programmers began creating M-system specifications.

At this time, IBM had not yet released an operating system capable of generalised multiprogramming. Earlier system architectures would have made this difficult. However, one of the FSD team, Martin Belsky, was a vocal advocate of making multiprogramming the technical basis for the operating systems 2. In September 1963 he managed to convince Reynolds and Ruthrauff that multiprogramming should be anticipated, and designed in from the start and he was recruited to take control of the development of the M6 control program. Belsky was not convinced that the M-systems were appropriate, but did not feel that he could write off all the work done so far.

So, at the end of 1963, the planning teams were creating a set of objectives for a multiprogramming control program, while development continued on the M-systems.

5. ANNOUNCEMENT AND CHANGES OF PLAN - 1963 to 1964

5.1. THE ANNOUNCEMENT

In April 1963, shortly after the reorganisation, Carl Reynolds conducted an assessment of the capabilities for developing the NPL software 2. It was concluded that it would not be ready for announcement until September 1964, with delivery dates of December 1965 for Romans I, II and II and 1966 for Roman IV. This would mean that the software would arrive several months after the processors. Also considered was a January 1964 announcement but Reynolds advised against this. Then, in September 1963, Reynolds changed his mind, and started supporting a March 1964 announcement 2, subsequently changed to 7th April 1964. This was supported by engineering managers and the DSD as a whole, despite an increased risk of late delivery, and the fact that the user manuals would not be ready until several months after that date. This recommendation was co-ordinated with other departments. This change, coupled with concerns of some DSD programmers, prompted a technical audit. The result was an indictment of the programming management, and the recomendation that a design task force should be established to determine the programming support objectives, to develop a system design and to formulate an implementation schedule. Reynolds considered the audit committee proposals, then formed a task force, with slightly different objectives to those recommended 2. Its terms of reference were to recommend whether the M-systems plan should be used or replaced with the plan developed by Belsky, and to produce basic designs and development assignments for the development laboratories. It was given three weeks to do this, instead of the twelve suggested by the audit committee. The task force was headed by Belsky, along with O. Scott Locken, the head of development for the 1410/7010 operating system. By mid-March 1964, the task force had made its report. The major recommendations were that multiprogramming, modularity of the control programs and disc storage were all to be accepted 2. There were also major advances in defining aspects of the control program. The task force also warned that the schedules were almost unattainable.The revised plan called for a single operating system with a modular control program, that could support a range of memory capabilities starting as low at 8K and going up to 512K 2. This operating system was called Operating System/360, or OS/360. A "Special Support" suite of programs would be provided for the System/360 Model 30, the only machine available with 8K of memory, which would contain assemblers, compilers and utilities, but would have no main control program, due to memory limitations. A release plan was also developed, giving release dates for all the proposed OS/360 components, starting in the third quarter of 1964 with one of the Special Support packages and ending in the second quarter of 1966 with the release of time-sharing software.

While the task force was meeting, there was also a staff reorganisation 2. Ruthrauff stepped down and was replaced by Brooks, whilst Belsky became the head of the design control function and Locken took over Belsky's job, of program implementation manager.

5.2. AFTER THE ANNOUNCEMENT

Once OS/360 had been announced, Reynolds was optimistic. There was finally a concrete technical plan and the arguments about control program structure and function seemed to be over. There was also a strong development team assigned to the control program 2. At this point in time, the main cloud on the horizon was a dispute with the GPD Endicott laboratory programmers led by James Frame. They were responsible for the Special Support programs, as well as a number of other OS/360 components. The original cause of the dispute, however, was Frame's diversion the previous winter of GPD programmers to develop software for the proposed 1401-S computer. The main problem at the time was Frame's unwillingness to name any of the programmers working on OS/360, saying instead that no one person's work was exclusively associated with OS/360. By the end of April, the GPD programmers working on OS/360 under Frame had been moved to DSD and placed under the control of Brooks. This happened just two weeks after the announcement. By October 1964, Frame had left and the group was moved back to DSD.

In May, however, the problems began again. It had been discovered that there were scheduling conflicts that would leave the project about sixty days behind schedule by the end of 1964 2. The major conflict was between the control program coding schedule (developed by Belsky) and the requirements of programmers who needed control program functional and interface information to develop their code (under the control of Locken). Belsky felt that the delays were the price of delivering good quality software, while Locken felt that he could speed things up. Brooks decided to return design authority to Locken, whilst leaving Belsky and his team as a design review team.

There were further resource problems by June 1964. There were two end of year milestones that needed to be achieved, publication of the user manuals and some in-house testing, to ensure that the design and development plan tallied with the specification. 2 Locken had split the development of the control program into about forty functional segments, each of which was a major program in its own right. Each of these functional segments had to be tested both individually and as part of the whole. The system test was scheduled for December 1964.

6. DEVELOPMENT AND RELEASE - 1964 to 1967

However, by mid-1964 other major problems were encountered, that would require yet more changes in the plan.

6.1. THE 16K MEMORY PROBLEM

By June 1964, it had been established that the OS/360 control program memory requirements were substantially higher than the allocated 6K. This would have severe repercussions for systems with 16K of memory. With disc based systems, a system for loading disc-based subroutines could be used, but this was not feasible for those systems with only tape-based storage. DSD proposed that disc support was widely enough accepted by users that tape support be omitted. GPD then produced a survey showing that 20% of orders for Model 30 systems with 16K of memory and larger were tape based systems with no disc storage 2. To further add to the problems, in October 1964 DSD ran a performance analysis of OS/360 on a 16K system 2. The results showed that the memory level might have to be abandoned totally. The end result of all the discussion was that GPD was to be responsible for "16K tape" and "16K disc" operating systems, as well as the Special Support packages - in other words, operating system support for the Model 30. The new operating systems had to be ready by late 1965, the time that OS/360 support was to have been released.

The changes were announced on the last day of 1964 2, for delivery in the third quarter of 1965. There were to be four operating systems. The first was BOS (Basic Operating System), which was for 8K systems. The next level consisted of two operating systems, TOS (Tape Operating System) and DOS (Disc Operating System), which were intended for tape-based and disc-based 16K systems. The top level of operating system was OS/360, for all computers with more than 16K of memory. The Special Support programs became BPS (Basic Programming Support) 1, 2. The BPS programs were released on schedule, between March and September 1965 2. BOS was released two weeks late, in October 1965. Of the three operating systems, DOS was the latest, being rescheduled first for March 1966, then finally released in June of that year.

There were still a number of problems that needed to be sorted out, partly to do with program compatibility 2. Some of the planned programs, such as the 10K assembler, needed to be able to run on TOS and DOS systems, as well as OS/360. There was also a mismatch between workload and programmers available. There was a large recruiting effort at the Endicott laboratory to support these activities, and laboratories at other GPD sites were also used to developed software.

DOS ended up being the most widely used operating system in the world 2. It went through twenty-six upgrades for System/360, and a version for systems with at least 32K of memory that allowed limited multiprogramming was available.

6.2. OS/360

In July 1964, a month after the resource and memory problems were encountered, another appraisal was carried out on the state of development. It was found that the December target for manual publication and testing was optimistic, and that it might take an additional three months to meet the targets 2. Into this situation came Richard Case, as the new assistant manager of OS/360, under Brooks. Case became part-time acting manager two months later, when Brooks took up a part time university post. Case's office became the focus of the attempts to design and document the OS/360 components 2. Locken placed the blame for failing to meet the target of the end of the year with Belsky's Design Control team, making an existing rift larger. By October, there was a growing feeling of desperation. Locken felt that Belsky's group should be dissolved and its members reassigned to programming teams. Belsky proposed moving the entire schedule back three months, and releasing a simpler interim control program. As October progressed, matters deteriorated further. Belsky's team were overwhelmed with draft specifications. Sometimes specifications were sent to Locken's programmers by the designers before they had been checked. This almost invariably resulted in major revisions taking place when the specification was finally checked.

By January 1965, a number of changes occurred. Firstly, Belsky's team was disbanded and the members assigned to programming roles. Secondly, there was an internal reorganisation of departments in IBM. GPD, DSD and the Components division were being reformed into the Systems Development Division (SDD) and the Systems Manufacturing Division 2. Reynolds was appointed director of programming. To replace Brooks, Frederick Trapnell, former director of IBM Hursley was recruited.

Locken's first task was to address a criticism made by Belsky that no enough use was being made of modularity with the control program design 2. The response was to develop a three-level supervisor and a two-level scheduler. The first useful combination was named the Primary Control Program (PCP). It consisted of the level 1 supervisor and level 1 scheduler, permitting sequential operation. The second combination, Multiprogramming with a Fixed Number of Tasks (MFT) consisted of the level 2 supervisor and either the level 1 or level 2 scheduler. This allowed simple multiprogramming to take place, with a fixed maximum number of tasks. The third and most advanced combination was Multiprogramming with a Variable Number of Tasks (MVT), comprising the level 3 supervisor and level 2 scheduler. It allowed full use to be made of the multiprogramming facilities of the computer. A plan was established that allowed the development of a number of versions of PCP between April and September 2. The control program was to be tested on System/360 hardware, as opposed to the emulators that had been used previously. This plan was soon changed as a result of design changes that had to be made. The new plan called for three series of versions, with the design changes being incorporated in the second and third series. This had a knock-on effect on the teams developing other OS/360 programs, such as compilers and assemblers. Tests of the second series started in June, and immediately there were more problems 2. The system was almost unusably slow. A plan was developed to fix this performance problem. At about this time, Reynolds and Trapnell realised that OS/360 delivery times would not be met, and at the end of August the release of PCP was rescheduled to March 1966, three months late.

The development of MFT and MVT were also affected. There was pressure for MFT to be dropped, whilest Locken argued much of the programming was already completed and it was easier for customers to convert to MFT than MVT 2. Eventually it was decided that only the more advanced of the two versions of MFT was to be dropped and the delivery date of the simpler version would be rescheduled to July 1967. MVT was rescheduled for November 1966, five months later than planned. By December, it was realised that there were some fundamental design problems with the MVT system. One of the main problems was that the memory was becoming too fragmented to be efficiently managed and by mid-January 1966, thirty specific problems had been isolated. A number of changes to the specification were made and alterations carried out. However, in April, following suggestions that the PCP performance problems be given the highest priority and MVT delayed further, the manager in charge resigned.

By the end of April PCP (OS/360 Release 1) had just been shipped and MVT had been rescheduled again 2. It was now to be released in the second quarter of 1967. MFT, which had nearly been killed off just six months earlier and had only been kept alive by the Data Processing Division programmers was to be released in November 1966. Fortunately, no further major problems were encountered. An interim version of MFT was released, followed soon after by the completed version. MVT finally emerged in August 1967. The second version of MFT, that had originally been scrapped completely, was eventually released by SDD in August 1968.

7. OS/360 CONSIDERED

The OS/360 project saga exhibits all that is bad in management of a large project. Although there are a number of large number of specific problems, underlying this there are several root causes. Specifically there appears to be no clear project management control and definition of responsibilities. Key elements of this were lack of a clear specification for software and a constantly changing definition of requirement, almost no planning, a total underestimate of the magnitude of the tasks being undertaken, and an inadequate allocation of appropriately trained staff in adequete numbers to the project. Although not discussed in this essay, all of these effects would have a significant impact on cost, leading to a massive overexpenditure.

For example, before the announcement of OS/360 in 1964, there were three completely different design plans at various times, the Romans, the M-systems and the modular system 2. This was disruptive to the members of the design team responsible for fleshing out the specification, and resulted in a lot of time being wasted in drawing up specifications for systems that were then not used. It is a classic error in project management not to allocate sufficent resources in the early part of a project to define a clear, unambiguous specification for what is required. A clear specification would not have allowed these problems to have occured in the OS/360 project.

The disagreements between the various teams developing the software should have been controlled by a project manager. The main ones were between GPD and DSD, over the allocation of programmers to the 1401-S and OS/360, and between Belsky and Locken, but there were numerous other conflicts, both on a personal level and between whole teams 2. Ultimately a project succeeds for fails because of the calibre and commitment of the staff deployed on it. It is acknowledged by Brooks that one of the reasons for the problems with the development of the OS/360 control programs was that the vast majority of the developers involved had only worked on one set of system programs before OS/360, mainly the 1410/7010 and Stretch 4. Brooks refers to this as the Second-System Effect and gives an example. A number of the parts of OS/360 were refined and embellished versions of bits taken from earlier operating systems. This includes the scheduler, which was taken from the 1410/7010 system. The basic design of the OS/360 scheduler is almost identical to its 1410/7010 counterpart, which was designed for batch mode operation, and makes things like multiprogramming difficult 4. Another part of this problem was the programmers' lack of experience with software of this size. OS/360 was the largest such project ever attempted at the time. The amount of memory that was initially allocated at the start of the design phase was soon doubled 2. Even then, there was a problem with systems that had 16K of memory. Although OS/360 would fit, it would not leave enough memory free to be able to do anything useful.

However, although the early releases of OS/360 were slow and filled with bugs, after several releases performance had improved and the number of problems was slowly decreasing 4. Some users, mainly those using DOS, PCP or MFT systems, experienced no real problems, especially if the software did not push the systems too hard 7. The main problem encountered by these users was security, and the need for at least 64K of memory to be able to usefully run MFT (although it could be run in 32K). For MVT users, however, it was a different story, with the operating system crashing frequently. It was the 1970's before MVT was as stable as PCP and MFT. It is interesting to note that although both DOS/360 and the MVT version of OS/360 were late, and MVT was filled with bugs, they became the two most popular operating systems for System/360, long outliving BOS, TOS, PCP and MFT, and eventually becoming two of the operating systems available for System/370.

8. CONCLUSION

The root cause of the OS/360 debacle was poor project management involving elements such as the lack of a clear specification, poor planning, an underestimate of the magnitude of the task and an inadequate allocation of appropriately trained staff. The lessons learnt from this debacle have now been learnt not only in the computer industry but in large projects in general, although even now when projects overrun or their costs escalate one or more of these causes are often the root of the problem.

REFERENCES

1. Amdahl, G.,  Blaauw, G., Brooks Jr, F. (1964) Architecture of the IBM System/360, IBM Journal of Research and Development, Volume 8, Number 2, pp. 87-101.

2. Aron, J.,  Brooks Jr, F., Evans, B. et al (1983) Discussion of the SPREAD Report, June 23, 1982, Annals of the History of Computing, Volume 5, Number 1, pp.27-44.

3. Brooks Jr, F. (1975) The Mythical Man-Month, Massachusetts: Addison-Wesley Publishing Company. Reprinted (1982) Massachusetts: Addison-Wesley Publishing Company.

4. Campbell-Kelly, M. and Asprey, W. (1996) Computer: A History of the Information Machine, New York: Basic Books.

5. Evans. B. (1983) Introduction to the SPREAD Report, Annals of the History of Computing, Volume , Number 1, pp. 4-5.

6. Evans, B. (1986) System/360: A Retrospective View, Annals of the History of Computing, Volume 8, Number 2, pp. 155-179.

7. Haanstra, J. et al (1961) Final Report of SPREAD Task Group. Reprinted Annals of the History of Computing 5, Number 1 (1983), pp. 6-26.

8. Private communication (1998) : J. Hodgskin, Recollections of a System/360 manager.

9. Pugh, E. W. et al (1991) IBM's 360 and early 370 computers, Cambridge, Mass.: MIT Press.